## Sheet1
Project | requirement ID | TC_ID | Module | Submodule | Scenario Description | Test Case Description | Step Description | Expected Result | Status | Remark | Defect ID | Defect Description | Defect Status | Created By | Tested By | Test Cases Designed Date | Test Cases Execution Date | No of Test Cases Executed | No of Test Case Reported | Defect Reopen Date | Defect Closed Date | Defect Closed Date
IDBI intech |  | TC001 | Customer Entitlement | User Maintenance | To verify if user is able to change Access Scheme | To check whether user is able to change access scheme to 'CORPAD' | Corporate Admin Dashboard>>Customer Entitlements>>User Maintenance>>Enter UserID>>Update | System should allow user to update Access Scheme to 'CORPAD' | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC002 | Corporate Administration | Corporate Administration | To verify Corporate administration option | To check whether 'Corporate Administration' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration | System should display 'Corporate Administration' option to user | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC003 | Corporate Administration | Corporate Administration | To verify Corporate administration option | To check whether user clicks on 'Corporate Administration' option | FEBA UAT Dashboard>>Menu>>Click on 'Corporate Administration' | System should display following options of the 'Corporate Administration': 1. Access Management 2. General Maintenance 3. Transactional Support 4. Administration Approvals 5. Recall Approval Request 6. Corporate Snapshot | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC004 | Corporate Administration | Access Management | To verify Access Management | To check whether 'Access Management' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management | System should display 'Access Management' option to user | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC005 | Corporate Administration | Access Management | To verify Access Management | To check whether user clicks on 'Access Management' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management | System should display following options of the 'Access Management': 1. Maintain User Access Details 2. Division Maintenance | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC006 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether 'Maintain User Access Details' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details | System should display 'Maintain User Access Details' option to user | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC007 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on 'Maintain User Access Details' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Maintain User Access Details' | System should display 'Maintain User Access Details' list | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC008 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check format for the displayed list of 'Maintain User Access Details' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Maintain User Access Details' | System should display the correct format for the 'Maintain User Access Details' list | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC009 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to create new user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Maintain User Access Details'>>Create New User | System should allow user to create new user | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC010 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether created user displays in 'Maintain User Access Details' list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Maintain User Access Details' | System should display the created user in the 'Maintain User Access Details' list | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC011 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check details for the displayed list of 'Maintain User Access Details' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Maintain User Access Details' | System should display the correct details for the 'Maintain User Access Details' list | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC012 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether logo displays the proper lable | FEBA UAT Dashboard>>Menu>>Maintain User Access Details>> Navigate on 'Blue' Logo | System should display the correct lable for the displayed logo | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC013 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on 'Corporate Master User ID' in the list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>'Maintain User Access Details>>Click on 'Corporate Master User ID' | System should display details of 'Corporate Master User ID' | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC014 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on the 'Back' Button on 'View Details page | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>'Maintain User Access Details>>Click on 'Corporate Master User ID' >>Click on 'Back' | System should allow user to navigate to the previous page | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC015 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on 'Access Scheme' in the list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Access Scheme' | System should display details of 'Menu Option Details' for selected Access Scheme | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC016 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on 'Entry & Approval Limit' in the list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' | System should display details of 'Entry & Approval Limit' for selected limit | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC017 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether 'Search' option for Entry & Approval Limits is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search | System should display 'Search' option for Entry & Approval Limits to user | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC018 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check format for 'Search' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search | System should display following format for the Search option: 1. Limit Scheme: <With limit data> 2. Transaction Type Dropdown 3. Limit Type Dropdown 4. Channel Type Dropdown 5. 'Search' Button 6. 'Clear' Button | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC019 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search limit by Transaction Type | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Transaction Type>>Search | User should able search limit by Transaction Type | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC020 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to view all Transaction Types in dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Transaction Type | System should display all transaction types in dropdown | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC021 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether all transaction types displays in alphabetical order | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Transaction Type | System should display all transaction types in alphabetical order | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC022 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search limit by Limit Type | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Limit Type>>Search | User should able search limit by Limit Type | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC023 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to view all Limit Types in dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Limit Type | System should display all Limit Types in dropdown | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC024 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether all Limit Types displays in alphabetical order | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Limit Type | System should display all Limit Types in alphabetical order | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC025 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search limit by Channel Type | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Channel Type>>Search | User should able search limit by Channel Type | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC026 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to view all Channel Types in dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Channel Type | System should display all Channel Types in dropdown | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC027 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether all Channel Types displays in alphabetical order | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Channel Type | System should display all Channel Types in alphabetical order | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC028 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search limit by selecting all details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Enter all details>>Search | User should able search limit by selecting all details | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC029 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear Transaction Type | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Transaction Type>>Clear | User should able to clear transaction type | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC030 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear Limit Type | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Limit Type>>Clear | User should able to clear limit type | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC031 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear Channel Type | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Channel Type>>Clear | User should able to clear channel type | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC032 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear all fields in search | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on 'Entry & Approval Limit' >>Search>> Enter all details>>Clear | User should able to clear all fields in search | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC033 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on 'More Actions' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions | System should display the following options for more actions: 1. Report Linkage 2. Set Password 3. User Channel Linkage 4. Copy User Details 5. Enable or Disable 6. Account Linkage 7. Customer ID Linkage 8. Edit or Delete Details 9. Menu Options Linkage | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC034 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to report linkage | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Report Linkage | System should allow user to report linkage | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC035 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to set Signon password | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Set Password | System should allow user to set Signon password | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC036 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to set Transaction password | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Set Password | System should allow user to set Transaction password | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC037 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to set Signon as well as Transaction password | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Set Password | System should allow user to set Signon as well as Transaction password | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC038 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to check user channel linkage | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>User Channel Linkage | System should allow user to check user channel linkage | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC039 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to create new user channel linkage | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>User Channel Linkage>>Create New | System should allow user to create new user channel linkage | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC040 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to update user channel linkage | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>User Channel Linkage>>Click on Three Dots in list>>Update | System should allow user to update user channel linkage | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-20
IDBI intech |  | TC041 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to delete user channel linkage | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>User Channel Linkage>>Click on Three Dots in list>>Delete | System should allow user to delete user channel linkage | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC042 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on the 'Back' Button on 'User Channel Linkage' page | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>User Channel Linkage>>Back | System should allow user to navigate to the previous page | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC043 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to copy user details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Copy User Details | System should allow user to copy user details | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC044 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to disable user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Enable or Disable | System should allow user to disable user | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC045 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to enable user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Enable or Disable | System should allow user to enable user | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC046 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to account linkage | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Account Linkage | System should allow user to account linkage | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC047 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to Customer ID linkage | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Customer ID Linkage | System should allow user to Customer ID linkage | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC048 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to edit details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Edit or Delete Details | System should allow user to edit details | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC049 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to delete details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Edit or Delete Details | System should allow user to delete details | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC050 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to Menu option linkage | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click on Three Dots 'More Actions>>Menu Option Linkage | System should allow user to Menu Option linkage | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC051 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether 'Search' option for Maintain User Access Details is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search | System should display 'Search' option for Maintain User Access Details to user | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC052 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check format for 'Search' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search | System should display following format for the Search option: 1. Master User ID 2. User First Name 3. User Last Name 4. Channel ID Dropdown 5. User Login ID 6. Primary Division with Dropdown 7. Mobile Number 8. 'Search' Button 9. 'Clear' Button | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC053 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search user access details by Master User ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Master User ID>>Search | User should able search user access details by Master User ID | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC054 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search user access details by User First Name | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>User First Name>>Search | User should able search user access details by User First Name | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC055 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search user access details by User Last Name | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>User Last Name>>Search | User should able search user access details by User Last Name | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC056 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search user access details by Channel ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Channel ID>>Search | User should able search user access details by Channel ID | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC057 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to view all Channel IDs in dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Channel ID | System should display all Channel IDs in dropdown | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC058 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether all Channel IDs displays in alphabetical order | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Channel ID | System should display all Channel IDs in alphabetical order | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC059 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search user access details by User Login ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>User Login ID>>Search | User should able search user access details by User Login ID | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC060 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search user access details by Primary Division | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Primary Division>>Search | User should able search user access details by Primary Division | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC061 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to view all Primary Division in dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Primary Division | System should display all Primary Division in dropdown | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC062 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether all Primary Division displays in alphabetical order | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Primary Division | System should display all Primary Division in alphabetical order | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC063 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search user access details by Mobile Number | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Mobile Number>>Search | User should able search user access details by Mobile Number | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC064 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to search user access details by selecting all details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>> Enter all details>>Search | User should able search user access details by selecting all details | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC065 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear Master User ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Master User ID>>Clear | User should able to clear Master User ID | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC066 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear User First Name | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>User First Name>>Clear | User should able to clear User First Name | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC067 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear User Last Name | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>User Last Name>>Clear | User should able to clear User Last Name | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC068 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear Channel ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Channel ID>>Clear | User should able to clear Channel ID | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC069 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear User Login ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>User Login ID>>Clear | User should able to clear User Login ID | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC070 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear Primary Division | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Primary Division>>Clear | User should able to clear Primary Division | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC071 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear Mobile Number | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Mobile Number>>Clear | User should able to clear Mobile Number | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC072 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to clear all fields in search | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Search>>Enter all Fields>>Clear | User should able to clear all fields in search | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC073 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user allows to search corporate user by page number | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Enter page number>>Go | System should allow user to search corporate user by page number | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC074 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on the 'Rows Per Page' dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click 'Rows Per Page' dropdown | System should display no. of entries per page | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC075 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to navigate to the next page on clicking on '>' (Next) | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click '>' | System should allow user to navigate to the next page | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC076 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is allows to navigate to the previous page on clicking on '<' (Previous) | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click '<' | System should allow user to navigate to the previous page | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC077 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether page number indicates after navigating from one page to another page | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click '>' or '<' | System should display page number after navigating from one page to another page | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC078 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on 'Multi-Record Action' dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click 'Multi-Record Action' dropdown | System should display the following options for 'Multi-Record Actions' : 1. Delete Users | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC079 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user allows to delete the corporate user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Maintain User Access Details>>Click 'Multi-Record Action' dropdown>> Select 'Delete Users' | System should allow to delete the corporate user | On Hold |  |  |  |  | Chitralekha Chavan |  | 2019-06-21
IDBI intech |  | TC080 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether 'Division Maintenance' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Division Maintenance | System should display 'Division Maintenance' option to user | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC081 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user clicks on 'Division Maintenance' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance' | System should display 'Division Maintenance' list | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC082 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check format for the displayed list of 'Division Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance' | System should display the correct format for the 'Division Maintenance' list | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC083 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check details for the displayed list of 'Division Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance' | System should display the correct details for the 'Division Maintenance' list | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC084 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to 'Create Division ID' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance'>>Click on 'Create New'>>Enter details>>Click on continue>>Click on submit | System should allow to user create new 'Division ID' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC085 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to view 'Create Division ID' in Division Maintainance list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance' | System should allow user to view 'Create Division ID' in Division Maintainance list | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC086 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether system display proper error messge while entered special character or Alphanumeric in Division ID fields to 'Create Division ID' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance'>>Click on 'Create New'>>Enter special character or Alphanumeric in Division ID >>Click on continue | System should display proper error messge while entered special character or Alphanumeric in Division ID fields to 'Create Division ID' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC087 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to 'Link Corporate User' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance'>>Click on more option>>Click on 'link or delink corporate user' | System should allow user is able to 'Link Corporate User' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC088 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to 'Delink Corporate User' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance'>>Click on more option>>Click on 'link or delink corporate user' | System should allow user is able to 'Delink Corporate User' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC089 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to 'Link Internal and External Accounts' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance'>>Click on more option>>Click on 'Link or Delink Internal and External Accounts' | System should allow user is able to 'Link Internal and External Accounts' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC090 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to 'Delink Internal and External Accounts' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance'>>Click on more option>>Click on 'Link or Delink Internal and External Accounts' | System should allow user is able to 'Delink Internal and External Accounts' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC091 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to Update'Division ID' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance'>>Click on more option>>Click on Update | System should allow user is able to Update 'Division ID' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC092 | Corporate Administration | Access Management | To verify if user is able to maintain access details | To check whether user is able to Delete 'Division ID' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Access Management>>Click on 'Division Maintenance'>>Click on more option>>Click on Delete | System should allow user is able to Delete 'Division ID' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-20
IDBI intech |  | TC093 | Corporate Administration | General Maintenance | To verify General Maintenance | To check whether 'General Maintenance' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>General Maintenance | System should display 'General Maintenance' option to user | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 3 | 3
IDBI intech |  | TC094 | Corporate Administration | General Maintenance | To verify General Maintenance | To check whether user clicks on 'General Maintenance' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Click on 'General Maintenance' | System should display following options of the 'General Maintenance': 1. Update Account Preferences | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 4 | 4
IDBI intech |  | TC095 | Corporate Administration | General Maintenance | To verify General Maintenance | To check whether 'Update Account Preferences' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences | System should display 'Update Account Preferences' option to user | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 4 | 4
IDBI intech |  | TC096 | Corporate Administration | General Maintenance | To verify General Maintenance | To check whether user clicks on 'Update Account Preferences' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences | System should display 'Update Account Preferences' list | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 5 | 5
IDBI intech |  | TC097 | Corporate Administration | General Maintenance | To verify General Maintenance | To check format for the displayed list of 'Update Account Preferences' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences | System should display the correct format for the 'Update Account Preferences | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 5 | 5
IDBI intech |  | TC098 | Corporate Administration | General Maintenance | To verify General Maintenance | To check details for the displayed list of 'Update Account Preferences' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences | System should display the correct details for the 'Update Account Preferences' list | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 5 | 5
IDBI intech |  | TC099 | Corporate Administration | General Maintenance | To verify General Maintenance | To check whether user clicks on 'Update Nickname' in the list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences>>Click on 'Update Nickname' | System should display details of 'MaintainAccount NIckname' screen | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 8 | 8
IDBI intech |  | TC100 | Corporate Administration | General Maintenance | To verify General Maintenance | To check details of 'Maintain Account Nickname' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences>>Click on 'Update Nickname' | System should Proper details of 'Maintain Account Nickname' | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 8 | 8
IDBI intech |  | TC101 | Corporate Administration | General Maintenance | To verify General Maintenance | To check whether user is able to 'Update Account Nickname' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences>>Click on 'Update Nickname'>>Enter nickname>>Click on continue>>Click on Submit | System should allow to user able to 'Update Account Nickname' | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 10 | 10
IDBI intech |  | TC102 | Corporate Administration | General Maintenance | To verify General Maintenance | To check whether user is able to navigate to next and previous page of 'Update Account Preferences' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences>>Click on next page and previous page | System should allow to user is able to navigate to next and previous page of 'Update Account Preferences' | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 7 | 7
IDBI intech |  | TC103 | Corporate Administration | General Maintenance | To verify General Maintenance | To check whether user is able to view Rows per page of 'Update Account Preferences' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences>>Click 'Rows per Page' | System should allow to user is able to view Rows per page of 'Update Account Preferences' | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 7 | 7
IDBI intech |  | TC104 | Corporate Administration | General Maintenance | To verify General Maintenance | To check whether user is able to search 'Update Account Preferences' by page number | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Update Account Preferences>>Enter page number>>Click on Go | System should allow to user is able to search 'Update Account Preferences' by page number | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-20 | 2019-06-25 | 7 | 7
IDBI intech |  | TC105 | Corporate Administration | Transactional Support | To verify Transactional support | To check whether 'Transactional Support' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support | System should display 'Transactional Support' option to user | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 2 | 2
IDBI intech |  | TC106 | Corporate Administration | Transactional Support | To verify Transactional support | To check whether user clicks on 'Transactional Support' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support | System should display following options of the 'Transactional Support': 1. Non-Financial Workflow Maintenance 2. User Role Maintenance 3. Rule Maintenance 4. Financial Workflow Maintenance | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 3 | 3
IDBI intech |  | TC107 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether 'User Role Maintenance' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>User Role Maintenance | System should display 'User Role Maintenance' option to user | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 3 | 3
IDBI intech |  | TC108 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user clicks on 'User Role Maintenance' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'User Role Maintenance' | System should display 'User Role Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 4 | 4
IDBI intech |  | TC109 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check format for the displayed list of 'User Role Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'User Role Maintenance' | System should display the correct format for the 'User Role Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 4 | 4
IDBI intech |  | TC110 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user is able to add new role | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'User Role Maintenance'>>Add Role | System should allow user to add new role | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 15 | 15
IDBI intech |  | TC111 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether created role displays in 'User Role Maintenance' list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'User Role Maintenance' | System should display the created role in the 'User Role Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 15 | 15
IDBI intech |  | TC112 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check details for the displayed list of 'User Role Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'User Role Maintenance' | System should display the correct details for the 'User Role Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 15 | 15
IDBI intech |  | TC113 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user clicks on 'Role Name' in the list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'User Role Maintenance'>>Click on 'Role Name' | System should display details of corporate role | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 15 | 15
IDBI intech |  | TC114 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user clicks on 'More Actions' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'User Role Maintenance'>>Click on Three Dots 'More Actions | System should display the following options for more actions: 1. Edit 2. Delete | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 5 | 5
IDBI intech |  | TC115 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user is allows to edit role | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'User Role Maintenance'>>Click on Three Dots 'More Actions>>Edit | System should allow user to edit role | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 12 | 12
IDBI intech |  | TC116 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user is allows to delete role | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'User Role Maintenance'>>Click on Three Dots 'More Actions>>Delete | System should allow user to delete role | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 9 | 9
IDBI intech |  | TC117 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether 'Search' option for User Role Maintenance is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>User Role Maintenance>>Search | System should display 'Search' option for User Role Maintenance to user | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 6 | 6
IDBI intech |  | TC118 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check format for 'Search' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>User Role Maintenance>>Search | System should display following format for the Search option: 1. Bank ID with label 2. Corporate ID with Label 3. Corporate Name with Label 4. Role Name 5. Role Hierarchy 6. 'Search' Button 7. 'Clear' Button | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC119 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user is able to search role details by Role Name | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>User Role Maintenance>>Search>>Role Name>>Search | User should able search role details by Role Name | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 10 | 10
IDBI intech |  | TC120 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user is able to search role details by Role Hierarchy | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>User Role Maintenance>>Search>>Role Hierarchy>>Search | User should able search role details by Role Hierarchy | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 10 | 10
IDBI intech |  | TC121 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user is able to search role details by selecting all details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>User Role Maintenance>>Search>> Enter all details>>Search | User should able search role details by selecting all details | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 10 | 10
IDBI intech |  | TC122 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user is able to clear Role Name | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>User Role Maintenance>>Search>>Role Name>>Clear | User should able to clear Role Name | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC123 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user is able to clear Role Hierarchy | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>User Role Maintenance>>Search>>Role Hierarchy>>Clear | User should able to clear Role Hierarchy | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC124 | Corporate Administration | Transactional Support | To verify if user is able to maintain user role | To check whether user is able to clear all fields in search | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>User Role Maintenance>>Search>>Enter all Fields>>Clear | User should able to clear all fields in search except Bank ID, Corporate ID, Corporate Name | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC125 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether 'Rule Maintenance' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance | System should display 'Rule Maintenance' option to user | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 3 | 3
IDBI intech |  | TC126 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user clicks on 'Rule Maintenance' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Rule Maintenance' | System should display 'Rule Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 5 | 5
IDBI intech |  | TC127 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check format for the displayed list of 'Rule Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Rule Maintenance' | System should display the correct format for the 'Rule Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 5 | 5
IDBI intech |  | TC128 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is able to add new Rule | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Rule Maintenance'>>Add Rule | System should allow user to add new Rule | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 11 | 11
IDBI intech |  | TC129 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether created Rule displays in 'Rule Maintenance' list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Rule Maintenance' | System should display the created Rule in the 'Rule Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 11 | 11
IDBI intech |  | TC130 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check details for the displayed list of 'Rule Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Rule Maintenance' | System should display the correct details for the 'Rule Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 11 | 11
IDBI intech |  | TC131 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user clicks on 'Back' button on 'Add Rules' page | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Rule Maintenance'>>Add Rule>>Click on 'Back' | System should allow user to navigate on previous page | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC132 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user allows to clear data on 'Add Rules' page | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Rule Maintenance'>>Add Rule>>Enter data>>Click on 'Clear' | System should allow user to clear entered data on 'Add Rules' page | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC133 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user clicks on 'More Actions' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Rule Maintenance'>>Click on Three Dots 'More Actions | System should display the following options for more actions: 1. Edit 2. Delete | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC134 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is allows to edit Rule | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Rule Maintenance'>>Click on Three Dots 'More Actions>>Edit | System should allow user to edit Rule | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 11 | 11
IDBI intech |  | TC135 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is allows to delete Rule | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Rule Maintenance'>>Click on Three Dots 'More Actions>>Delete | System should allow user to delete Rule | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 10 | 10
IDBI intech |  | TC136 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether 'Search' option for Rule Maintenance is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search | System should display 'Search' option for Rule Maintenance to user | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC137 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check format for 'Search' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search | System should display following format for the Search option: 1. Bank ID with label 2. Corporate ID with Label 3. Role Description with Dropdown 4. Follow Hierarchy with Dropdown 5. 'Search' Button 6. 'Clear' Button | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC138 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is able to search Rule details by Role Description | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>>Role Description>>Search | User should able search Rule details by Role Description | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 9 | 9
IDBI intech |  | TC139 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is able to view all rules in dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>>Role Description | System should display all rules in dropdown | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC140 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether all rules displays in alphabetical order | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>>Role Description | System should display all rules in alphabetical order | Fail |  | D146_TC140 | System not show role Description in alphabetical order |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC141 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is able to search Rule details by Follow Hierarchy | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>>Follow Hierarchy>>Search | User should able search Rule details by Follow Hierarchy | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 9 | 9
IDBI intech |  | TC142 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is able to view 'Yes' or 'No' rule hierarchy in dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>>Follow Hierarchy | System should display 'Yes' or 'No' rule hierarchy in dropdown | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC143 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether hierarchy displays in alphabetical order | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>>Follow Hierarchy | System should display hierachy in alphabetical order | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC144 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is able to search Rule details by selecting all details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>> Enter all details>>Search | User should able search Rule details by selecting all details | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 9 | 9
IDBI intech |  | TC145 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is able to clear Role Description | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>>Rule Name>>Clear | User should able to clear Rule Name | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 9 | 9
IDBI intech |  | TC146 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is able to clear Follow Hierarchy | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>>Follow Hierarchy>>Clear | User should able to clear Follow Hierarchy | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC147 | Corporate Administration | Transactional Support | To verify if user is able to maintain user rule | To check whether user is able to clear all fields in search | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Rule Maintenance>>Search>>Enter all Fields>>Clear | User should able to clear all fields in search except Bank ID, Corporate ID | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC148 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether 'Financial Workflow Maintenance' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Financial Workflow Maintenance | System should display 'Financial Workflow Maintenance' option to user | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 3 | 3
IDBI intech |  | TC149 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user clicks on 'Financial Workflow Maintenance' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Financial Workflow Maintenance' | System should display 'Financial Workflow Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 5 | 5
IDBI intech |  | TC150 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check format for the displayed list of 'Financial Workflow Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Financial Workflow Maintenance' | System should display the correct format for the 'Financial Workflow Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 5 | 5
IDBI intech |  | TC151 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user clicks on 'Transaction Type' in the list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Financial Workflow Maintenance'>>Click on 'Transaction Type' | System should display details of 'Financial Workflow' | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC152 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user is able to add new financial workflow | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Financial Workflow Maintenance'>>Add Workflow | System should allow user to add new financial workflow | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 13 | 13
IDBI intech |  | TC153 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether created workflow displays in 'Financial Workflow Maintenance' list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Financial Workflow Maintenance' | System should display the created Workflow in the 'Financial Workflow Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 13 | 13
IDBI intech |  | TC154 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check details for the displayed list of 'Financial Workflow Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Financial Workflow Maintenance' | System should display the correct details for the 'Financial Workflow Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 13 | 13
IDBI intech |  | TC155 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user clicks on 'Back' button on 'Add Workflow' page | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Financial Workflow Maintenance'>>Add Workflow>>Click on 'Back' | System should allow user to navigate on previous page | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC156 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user clicks on 'More Actions' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Financial Workflow Maintenance'>>Click on Three Dots 'More Actions | System should display the following options for more actions: 1. Edit 2. Delete | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 6 | 6
IDBI intech |  | TC157 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user is allows to edit financial workflow | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Financial Workflow Maintenance'>>Click on Three Dots 'More Actions>>Edit | System should allow user to edit financial workflow | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 11 | 11
IDBI intech |  | TC158 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user is allows to delete financial workflow | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Financial Workflow Maintenance'>>Click on Three Dots 'More Actions>>Delete | System should allow user to delete financial workflow | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 10 | 10
IDBI intech |  | TC159 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user allows to search financial workflow by page number | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Financial Workflow Maintenance'>>Enter page number>>Go | System should allow user to search financial workflow by page number | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC160 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user clicks on the 'Rows Per Page' dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Financial Workflow Maintenance'>>Click 'Rows Per Page' dropdown | System should display no. of entries per page | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC161 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user is allows to navigate to the next page on clicking on '>' (Next) | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Financial Workflow Maintenance'>>Click '>' | System should allow user to navigate to the next page | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC162 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether user is allows to navigate to the previous page on clicking on '<' (Previous) | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Financial Workflow Maintenance'>>Click '<' | System should allow user to navigate to the previous page | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC163 | Corporate Administration | Transactional Support | To verify if user is able to maintain financial Workflow | To check whether page number indicates after navigating from one page to another page | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Financial Workflow Maintenance'>>Click '>' or '<' | System should display page number after navigating from one page to another page | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC164 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether 'Non-Financial Workflow Maintenance' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Non-Financial Workflow Maintenance | System should display 'Non-Financial Workflow Maintenance' option to user | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 4 | 4
IDBI intech |  | TC165 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user clicks on 'Non-Financial Workflow Maintenance' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Non-Financial Workflow Maintenance' | System should display 'Non-Financial Workflow Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 5 | 5
IDBI intech |  | TC166 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check format for the displayed list of 'Non-Financial Workflow Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Non-Financial Workflow Maintenance' | System should display the correct format for the 'Non-Financial Workflow Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 5 | 5
IDBI intech |  | TC167 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user clicks on 'Transaction Type' in the list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Click on 'Transaction Type' | System should display details of 'Non-Financial Workflow' | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC168 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user is able to add new non-financial workflow | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Non-Financial Workflow Maintenance'>>Create New | System should allow user to add new non-financial workflow | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 11 | 11
IDBI intech |  | TC169 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether created workflow displays in 'Non-Financial Workflow Maintenance' list | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Non-Financial Workflow Maintenance' | System should display the created Workflow in the 'Non-Financial Workflow Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 11 | 11
IDBI intech |  | TC170 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check details for the displayed list of 'Non-Financial Workflow Maintenance' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Non-Financial Workflow Maintenance' | System should display the correct details for the 'Non-Financial Workflow Maintenance' list | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 11 | 11
IDBI intech |  | TC171 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user clicks on 'Back' button on 'Create New' page | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>Click on 'Non-Financial Workflow Maintenance'>>Create New>>Click on 'Back' | System should allow user to navigate on previous page | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC172 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user is allows to delete non-financial workflow | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Delete | System should allow user to delete non-financial workflow | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 10 | 10
IDBI intech |  | TC173 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether 'Search' option for Non-Financial Workflow Maintenance is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Search | System should display 'Search' option for Non-Financial Workflow Maintenance to user | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 6 | 6
IDBI intech |  | TC174 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check format for 'Search' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Search | System should display following format for the Search option: 1. Bank ID with label 2. Corporate ID with Label 3. Transaction Type with Dropdown 4. 'Search' Button 5. 'Clear' Button | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 7 | 7
IDBI intech |  | TC175 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user is able to search Non-Financial Workflow details by Transaction Type | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Search>>Transaction Type>>Search | User should able search Non-Financial Workflow details by Transaction Type | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 9 | 9
IDBI intech |  | TC176 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user is able to view all Transaction Types in dropdown | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Search>>Transaction Type | System should display all Transaction Types in dropdown | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC177 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether all Transaction Types displays in alphabetical order | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Search>>Transaction Type | System should display all Transaction Types in alphabetical order | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 8 | 8
IDBI intech |  | TC178 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user is able to search Non-Financial Workflow details by selecting all details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Search>> Enter all details>>Search | User should able search Non-Financial Workflow details by selecting all details | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 10 | 10
IDBI intech |  | TC179 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user is able to clear Transaction Type | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Search>>Transaction Type>>Clear | User should able to clear Transaction Type | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 9 | 9
IDBI intech |  | TC180 | Corporate Administration | Transactional Support | To verify if user is able to maintain non-financial Workflow | To check whether user is able to clear all fields in search | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Non-Financial Workflow Maintenance'>>Search>>Enter all Fields>>Clear | User should able to clear all fields in search except Bank ID, Corporate ID | Pass |  |  |  |  | Chitralekha Chavan | Rajesh Magdum | 2019-06-21 | 2019-06-24 | 9 | 9
IDBI intech |  | TC181 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether 'Administration Approvals' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approvals | System should display 'Administration Approvals' option to user | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 3 | 3
IDBI intech |  | TC182 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user clicks on 'Administration Approvals' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approvals | System should display 'Administration Approvals' list | Fail |  | TOL ID-851413 | Access Management: System not allows to create new user without selecting ‘Scheme ID’ with error message “Select the scheme ID.” which is not shows as mandatory field even after clicking on ‘LOOKUP’ of ‘Scheme ID’ it gives error message as “The scheme IDs cannot be fetched.” |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21
IDBI intech |  | TC183 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check format for the displayed list of 'Administration Approvals' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approvals | System should display the correct format for the 'Administration Approvals' list | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC184 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check details for the displayed list of 'Administration Approvals' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approvals | System should display the correct details for the 'Administration Approvals' list | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC185 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user allows to approve transaction | EBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approvals>>Approve transaction | System should allow user to approve transaction | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC186 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether 'Search' option for Administration Approvals is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approvals>>Search | System should display 'Search' option forAdministration Approvals to user | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 5 | 5
IDBI intech |  | TC187 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check format for 'Search' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approvals'>>Search | System should display following format for the Search option: 1. From date and To date 2. Task with dropdown 3. Requested by with Lookup 4.Reference ID From and To 5. 'Search' Button 6. 'Clear' Button | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 6 | 6
IDBI intech |  | TC188 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to search Administration Approval details by From date and To date | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approval>>Search>>From date and To date>>Search | User should able search Administration Approval details by From date and To date | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC189 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to search Administration Approval details by Task | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approval>>Search>>Task>>Search | User should able search Administration Approval details by Task | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC190 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to search Administration Approval details by Requested By with Lookup | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approval>>Search>> Requested By with Lookup>>Search | User should able search Administration Approval details Requested By with Lookup | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC191 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to search Administration Approval details by From Reference ID and To Reference ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approval>>Search>>From Reference ID and To Reference ID>>Search | User should able search Administration Approval details by From Reference ID and To Reference ID | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC192 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to clear From date | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Administration Approval'>>Search>>From Date>>Clear | User should able to clear From date | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 8 | 8
IDBI intech |  | TC193 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to clear To date | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Administration Approval'>>Search>>To Date>>Clear | User should able To clear From date | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 8 | 8
IDBI intech |  | TC194 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to clear Task | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Administration Approval'>>Search>>Task>>Clear | User should able To clear Task | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 8 | 8
IDBI intech |  | TC195 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to clear Requested by | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Administration Approval'>>Search>>Requested by>>Clear | User should able To clear Requested by | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 8 | 8
IDBI intech |  | TC196 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to clear From Reference ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Administration Approval'>>Search>>From Reference ID>>Clear | User should able To clear From Reference ID | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 8 | 8
IDBI intech |  | TC197 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to clear To Reference ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Administration Approval'>>Search>>To Reference ID>>Clear | User should able To clear To Reference ID | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 8 | 8
IDBI intech |  | TC198 | Corporate Administration | Administration Approvals | To verify Administration Approvals | To check whether user is able to clear all fields in search | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Administration Approval'>>Search >>Enter details>>Clear | User should able to clear all fields in search | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 8 | 8
IDBI intech |  | TC199 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether 'Recall Approval Requests' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Recall Approval Requests | System should display 'Recall Approval Requests' option to user | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 3 | 3
IDBI intech |  | TC200 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user clicks on 'Recall Approval Requests' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Recall Approval Requests | System should display 'Recall Approval Requests' list | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC201 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check format for the displayed list of 'Recall Approval Requests' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Recall Approval Requests | System should display the correct format for the 'Recall Approval Requests' list | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC202 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check details for the displayed list of 'Recall Approval Requests' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Recall Approval Requests | System should display the correct details for the 'Recall Approval Requests' list | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC203 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user allows to Recall Approval Requests | EBA UAT Dashboard>>Menu>>Corporate Administration>>Administration Approvals>>Recall Approval Requests | System should allow user to Recall Approval Requests | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC204 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether 'Search' option for Recall Approval Requests is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>> Recall Approval Requests>>Search | System should display 'Search' option for Recall Approval Requests to user | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 4 | 4
IDBI intech |  | TC205 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check format for 'Search' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>> Recall Approval Requests>>Search | System should display following format for the Search option: 1. From date and To date 2. Task with dropdown 3.Reference ID From and To 4. 'Search' Button 5. 'Clear' Button | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 5 | 5
IDBI intech |  | TC206 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user is able to search Recall Approval Request details by From date and To date | FEBA UAT Dashboard>>Menu>>Corporate Administration>> Recall Approval Request>>Search>>From date and To date>>Search | User should able search Recall Approval Request by From date and To date | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC207 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user is able to search Recall Approval Request details by Task | FEBA UAT Dashboard>>Menu>>Corporate Administration>> Recall Approval Requests>>Search>>Task>>Search | User should able search Recall Approval Request details by Task | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC208 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user is able to search Recall Approval Request details by From Reference ID and To Reference ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Recall Approval Request>>Search>>From Reference ID and To Reference ID>>Search | User should able search Recall Approval Request details by From Reference ID and To Reference ID | On Hold | TOL ID-851413 |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC209 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user is able to clear From date | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Recall Approval Requests'>>Search>>From Date>>Clear | User should able to clear From date | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 7 | 7
IDBI intech |  | TC210 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user is able to clear To date | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Recall Approval Requests'>>Search>>To Date>>Clear | User should able To clear From date | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 7 | 7
IDBI intech |  | TC211 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user is able to clear Task | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Recall Approval Requests'>>Search>>Task>>Clear | User should able To clear Task | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 7 | 7
IDBI intech |  | TC212 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user is able to clear From Reference ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Recall Approval Request'>>Search>>From Reference ID>>Clear | User should able To clear From Reference ID | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 7 | 7
IDBI intech |  | TC213 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user is able to clear To Reference ID | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Recall Approval Request'>>Search>>To Reference ID>>Clear | User should able To clear To Reference ID | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 7 | 7
IDBI intech |  | TC214 | Corporate Administration | Recall Approval Requests | To verify Recall Approval Requests | To check whether user is able to clear all fields in search | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Transactional Support>>'Recall Approval Requests'>>Search >>Enter details>>Clear | User should able to clear all fields in search | Pass |  |  |  |  | Rajesh Magdum | Rajesh Magdum | 2019-06-21 | 2019-06-25 | 7 | 7
IDBI intech |  | TC215 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether 'Corporate snapshots' option is available to user | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display 'Corporate snapshots' option to user | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC216 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on 'Corporate snapshots' option | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display 'Corporate snapshots' list | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC217 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check format for the displayed list of 'Corporate snapshots' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display the correct format for the 'Corporate snapshots' list | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC218 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check details for the displayed list of 'Corporate snapshots' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display the correct details for the 'Corporate snapshots' list | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC219 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check format for user details with correct details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display proper format for user details with correct details | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC220 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user allows to search corporate user by page number | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots'>>In user details Enter page number>>Go | System should allow user to search corporate user by page number | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC221 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on the 'Rows Per Page' dropdown | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Entry / Approval Limit Scheme'>>Click 'Rows Per Page' dropdown | System should display no. of entries per page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC222 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user is allows to navigate to the next page on clicking on '>' (Next) | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click '>' | System should allow user to navigate to the next page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC223 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user is allows to navigate to the previous page on clicking on '<' (Previous) | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click '<' | System should allow user to navigate to the previous page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC224 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether page number indicates after navigating from one page to another page | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click '>' or '<' | System should display page number after navigating from one page to another page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC225 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on 'Entry / Approval Limit Scheme' | FEBA UAT Dashboard>>Menu>>Corporate Administration>> ' Entry / Approval Limit Scheme' | System should display ' Entry / Approval Limit Scheme' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC226 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check details for the displayed list of 'Entry / Approval Limit Scheme' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Entry / Approval Limit Scheme' | System should display the correct details for the 'Entry / Approval Limit Scheme' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC227 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user allows to search transaction by page number | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Entry / Approval Limit Scheme'>>Enter page number>>Go | System should allow user to search transaction by page number | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC228 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on the 'Rows Per Page' dropdown | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Entry / Approval Limit Scheme'>>Click 'Rows Per Page' dropdown | System should display no. of entries per page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC229 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user is allows to navigate to the next page on clicking on '>' (Next) | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Entry / Approval Limit Scheme'>>Click '>' | System should allow user to navigate to the next page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC230 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user is allows to navigate to the previous page on clicking on '<' (Previous) | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Entry / Approval Limit Scheme'>>Click '<' | System should allow user to navigate to the previous page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC231 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether page number indicates after navigating from one page to another page | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Entry / Approval Limit Scheme'>>Click '>' or '<' | System should display page number after navigating from one page to another page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC232 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether system navigtae to previous screen on click on 'Back'button | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Entry / Approval Limit Scheme'>>Click on 'Back' | System should navigtae to previous screen on click on 'Back'button | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC233 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check format for transaction limit with correct details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display proper format fortransaction limit with correct details | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC234 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on 'Daily Transaction Limit' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>'Daily Transaction Limit' | System should display 'Daily Transaction Limit' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC235 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check details for the displayed list of 'Daily Transaction Limit' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>'Daily Transaction Limit' | System should display the correct details for the 'Daily Transaction Limit' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC236 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user allows to search transaction by page number | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Daily Transaction Limit'>>Enter page number>>Go | System should allow user to search transaction by page number | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC237 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on the 'Rows Per Page' dropdown | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on'Daily Transaction Limit'>>Click 'Rows Per Page' dropdown | System should display no. of entries per page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC238 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user is allows to navigate to the next page on clicking on '>' (Next) | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Daily Transaction Limit'>>Click '>' | System should allow user to navigate to the next page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC239 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user is allows to navigate to the previous page on clicking on '<' (Previous) | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on'Daily Transaction Limit'>>Click '<' | System should allow user to navigate to the previous page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC240 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether page number indicates after navigating from one page to another page | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on'Daily Transaction Limit'>>Click '>' or '<' | System should display page number after navigating from one page to another page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC241 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether system navigtae to previous screen on click on 'Back'button | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on'Daily Transaction Limit'>>Click on 'Back' | System should navigtae to previous screen on click on 'Back'button | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC242 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check format for 'ROLE DEFINITION' with correct details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display proper format for 'ROLE DEFINITION' with correct details | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC243 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on 'Role Name' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>> Click on 'Role ID/name' | System should display'Corporate Role Details' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC244 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check details for the 'Corporate Role Details' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>'Role ID/Name' | System should display the correct 'Corporate Role Details' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC245 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether system navigtae to previous screen on click on 'Back'button | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>Click on 'Role ID/name'>>Click on 'Back' | System should navigtae to previous screen on click on 'Back'button | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC246 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check format for 'CORPORATE NON-FINANCIAL WORKFLOW RULES' with correct details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display proper format for 'CORPORATE NON-FINANCIAL WORKFLOW RULES' with correct details | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC247 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check details for 'CORPORATE NON-FINANCIAL WORKFLOW RULES' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display the correct details for the'CORPORATE NON-FINANCIAL WORKFLOW RULES' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC248 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on 'Transaction Type' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>> Click on'Transaction Type' | System should display 'Non-Financial Workflow Details' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC249 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check details for the 'Non-Financial Workflow Details' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on'Transaction Type' | System should display the correct 'Non-Financial Workflow Details' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC250 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether system navigtae to previous screen on click on 'Back'button | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>Click on'Transaction Type'>>Click on 'Back' | System should navigtae to previous screen on click on 'Back'button | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC251 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check format for 'CORPORATE FINANCIAL WORKFLOW RULES' with correct details | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots | System should display proper format for 'CORPORATE FINANCIAL WORKFLOW RULES' with correct details | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC252 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user allows to search transaction by page number | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Daily Transaction Limit'>>Enter page number>>Go | System should allow user to search transaction by page number | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC253 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on the 'Rows Per Page' dropdown | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on'Daily Transaction Limit'>>Click 'Rows Per Page' dropdown | System should display no. of entries per page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC254 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user is allows to navigate to the next page on clicking on '>' (Next) | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on 'Daily Transaction Limit'>>Click '>' | System should allow user to navigate to the next page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC255 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user is allows to navigate to the previous page on clicking on '<' (Previous) | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on'Daily Transaction Limit'>>Click '<' | System should allow user to navigate to the previous page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC256 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether page number indicates after navigating from one page to another page | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on'Daily Transaction Limit'>>Click '>' or '<' | System should display page number after navigating from one page to another page | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC257 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether user clicks on 'Transaction Type' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>> Click on'Transaction Type' | System should display 'Financial Workflow Details' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC258 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check details for the 'Financial Workflow Details' | FEBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>> Click on'Transaction Type' | System should display the correct 'Financial Workflow Details' | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21
IDBI intech |  | TC259 | Corporate Administration | Corporate snapshots | To verify Corporate snapshots | To check whether system navigtae to previous screen on click on 'Back'button | EBA UAT Dashboard>>Menu>>Corporate Administration>>Corporate snapshots>>Click on'Transaction Type'>>Click on 'Back' | System should navigtae to previous screen on click on 'Back'button | On Hold |  |  |  |  | Rajesh Magdum |  | 2019-06-21

## Sheet2
25
66