## Sheet1
Project | requirement ID | TC_ID | Module | Submodule |  | Scenario Description | Test Case Description | Step Description | Expected Result | Status | Remark (Old Comments) | Defect ID | Defect Description | Defect Status | Tested By | Test Cases Designed Date | Test Cases Execution Date | No of Test Cases Executed | No of Test Case Reported | Defect Reopen Date | Defect Closed Date | Phase2 Test Cases Execution Date
IDBI intech |  | TC001 | Customer Entitlements | Corporate Maintenance | Corporate Maintenance | To verify if user is able to set personalized corporate limit for Corporate ID | To check whether user is able to set personalized corporate limit for Corporate ID(Rs. 500) for 'Payment' transaction type | ADMIN Dashboard>>Customer Entitlements>>Corporate Maintenance>>Enter Corporate Id>>Search>>Select 'Personalized Corporate Limit' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized corporate limit for Corporate ID for 'Payment' transaction type | Pass | [5 empty] | 2019-06-28 | 2019-06-28 | 10 | 10
IDBI intech |  | TC002 | Customer Entitlements | User Maintenance | User Maintenance | To verify if user is able to set personalized limit for Corporate User | To check whether user is able to set personalized limits for Corporate user(Rs. 600) for Payment transaction type | ADMIN Dashboard>>Customer Entitlements>>User Maintenance>>Enter User Login ID Details>>Search>>Select 'Personalized Limits' from 'More Actions' Dropdown>>OK>>Create New | System should not allow user to set personalized limits for Corporate user more than corporate ID limit as it shows proper error message | Pass | [5 empty] | 2019-06-28 | 2019-06-28 | 7 | 7
IDBI intech |  | TC003 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of beyond corporate limit (Rs. 510) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer of beyond corporate limit and display proper error message | Pass | It is working Now. Hence,Closed | D100 | Payment & Transfer (Personalize Corporate Limit): System allows to do fund transfer of beyond corporate limit. (Personalize Corporate Daily Limit is set to 500 and transaction amount is 510) | Closed |  | 2019-06-28 | 2019-06-28 | 7 | 7 | 2019-07-04 | 2019-07-05
IDBI intech |  | TC004 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of below corporate limit (Rs. 20) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should allow user to do fund transfer of below corporate limit | Pass | It is working Now. Hence,Closed | D101 | Payment & Transfer (Personalize Corporate Limit): System not allows to do fund transfer of below corporate limit as it gives error message as “The daily amount limit is exceeded” (Personalize Corporate Daily Limit is set to 500 and transaction amount is 20) | Closed |  | 2019-06-28 | 2019-07-05 | 5 | 5 |  | 2019-07-11
IDBI intech |  | TC005 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer when daily limit exceeded (Daily Limit remains 0) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer when daily limit exceeded and display proper error message | Pass | [5 empty] | 2019-06-28 | 2019-07-12 | 6 | 6
IDBI intech |  | TC006 | Payment & Transfer | Corporate Maintenance | Corporate Maintenance | To verify if user is able to set personalized corporate limit for Corporate ID | To check whether user is able to set personalized corporate limit for Corporate ID(Rs. 600) for 'Payment' transaction type | ADMIN Dashboard>>Customer Entitlements>>Corporate Maintenance>>Enter Corporate Id>>Search>>Select 'Personalized Corporate Limit' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized corporate limit for Corporate ID for 'Payment' transaction type | On Hold | [5 empty] | 2019-06-28
IDBI intech |  | TC007 | Customer Entitlements | User Maintenance | User Maintenance | To verify if user is able to set personalized limit for Corporate User | To check whether user is able to set personalized limits for Corporate user(Rs. 500) for 'Payment' transaction type | ADMIN Dashboard>>Customer Entitlements>>User Maintenance>>Enter User Login ID Details>>Search>>Select 'Personalized Limits' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized limits for Corporate user for payment transaction type | On Hold | [5 empty] | 2019-06-28
IDBI intech |  | TC008 | Customer Entitlements | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of beyond user personalised limit (Rs. 510) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer of beyond user personalised limit and display proper error message | On Hold | [5 empty] | 2019-06-28
IDBI intech |  | TC009 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of below user personalised limit (Rs. 20) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should allow user to do fund transfer of below user personalised limit | On Hold | [5 empty] | 2019-06-28
IDBI intech |  | TC010 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer when daily user personalized limit exceeded (Daily Limit remains 0) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer when daily user personalized limit exceeded and display proper error message | On Hold | [5 empty] | 2019-06-28
IDBI intech |  | TC011 | Payment & Transfer | Corporate Maintenance | Corporate Maintenance | To verify if user is able to set personalized corporate limit for Corporate ID | To check whether user is able to set personalized corporate limit for Corporate ID(Rs. 500) for 'Payment' transaction type | ADMIN Dashboard>>Customer Entitlements>>Corporate Maintenance>>Enter Corporate Id>>Search>>Select 'Personalized Corporate Limit' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized corporate limit for Corporate ID for 'Payment' transaction type | On Hold | [5 empty] | 2019-06-28
IDBI intech |  | TC012 | Payment & Transfer | User Maintenance | User Maintenance | To verify if user is able to set personalized limit for Corporate User | To check whether user is able to set personalized limits for Corporate user(Rs. 500) for 'Payment' transaction type | ADMIN Dashboard>>Customer Entitlements>>User Maintenance>>Enter User Login ID Details>>Search>>Select 'Personalized Limits' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized limits for Corporate user for payment transaction type | On Hold | [5 empty] | 2019-06-28
IDBI intech |  | TC013 | Customer Entitlements | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of beyond corporate and user personalised limit (Rs. 510) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer of beyond corporate and user personalised limit and display proper error message | On Hold | [5 empty] | 2019-06-28
IDBI intech |  | TC014 | Customer Entitlements | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of below corporate and user personalised limit (Rs. 20) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should allow user to do fund transfer of below corporate and user personalised limit | On Hold | [5 empty] | 2019-06-28
IDBI intech |  | TC015 | Paayment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer when daily corporate and user personalized limit exceeded (Daily Limit remains 0) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer when daily corporate and user personalized limit exceeded and display proper error message | On Hold
IDBI intech |  | TC016 | Customer Entitlements | Corporate Maintenance | Corporate Maintenance | To verify if user is able to set personalized corporate limit for Corporate ID | To check whether user is able to set personalized corporate limit for Corporate ID(Rs. 500) for 'Fund Transfer' transaction type | ADMIN Dashboard>>Customer Entitlements>>Corporate Maintenance>>Enter Corporate Id>>Search>>Select 'Personalized Corporate Limit' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized corporate limit for Corporate ID for 'Fund Transfer' transaction type | pass |  |  |  |  | Shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC017 | Customer Entitlements | User Maintenance | User Maintenance | To verify if user is able to set personalized limit for Corporate User | To check whether user is able to set personalized limits for Corporate user(Rs. 600) for Payment transaction type | ADMIN Dashboard>>Customer Entitlements>>User Maintenance>>Enter User Login ID Details>>Search>>Select 'Personalized Limits' from 'More Actions' Dropdown>>OK>>Create New | System should not allow user to set personalized limits for Corporate user more than corporate ID limit as it shows proper error message | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC018 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of beyond corporate limit (Rs. 510) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer of beyond corporate limit and display proper error message | pass |  |  |  |  | Shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC019 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of below corporate limit (Rs. 20) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should allow user to do fund transfer of below corporate limit | pass |  |  |  |  | Shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC020 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer when daily limit exceeded (Daily Limit remains 0) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer when daily limit exceeded and display proper error message | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC021 | Payment & Transfer | Corporate Maintenance | Corporate Maintenance | To verify if user is able to set personalized corporate limit for Corporate ID | To check whether user is able to set personalized corporate limit for Corporate ID(Rs. 600) for 'Fund Transfer' transaction type | ADMIN Dashboard>>Customer Entitlements>>Corporate Maintenance>>Enter Corporate Id>>Search>>Select 'Personalized Corporate Limit' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized corporate limit for Corporate ID for 'Fund Transfer' transaction type | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC022 | Customer Entitlements | User Maintenance | User Maintenance | To verify if user is able to set personalized limit for Corporate User | To check whether user is able to set personalized limits for Corporate user(Rs. 500) for 'Fund Transfer' transaction type | ADMIN Dashboard>>Customer Entitlements>>User Maintenance>>Enter User Login ID Details>>Search>>Select 'Personalized Limits' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized limits for Corporate user for payment transaction type | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC023 | Customer Entitlements | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of beyond user personalised limit (Rs. 510) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer of beyond user personalised limit and display proper error message | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC024 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of below user personalised limit (Rs. 20) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should allow user to do fund transfer of below user personalised limit | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC025 | Payment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer when daily user personalized limit exceeded (Daily Limit remains 0) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer when daily user personalized limit exceeded and display proper error message | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC026 | Payment & Transfer | Corporate Maintenance | Corporate Maintenance | To verify if user is able to set personalized corporate limit for Corporate ID | To check whether user is able to set personalized corporate limit for Corporate ID(Rs. 500) for 'Fund Transfer' transaction type | ADMIN Dashboard>>Customer Entitlements>>Corporate Maintenance>>Enter Corporate Id>>Search>>Select 'Personalized Corporate Limit' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized corporate limit for Corporate ID for 'Fund Transfer' transaction type | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC027 | Payment & Transfer | User Maintenance | User Maintenance | To verify if user is able to set personalized limit for Corporate User | To check whether user is able to set personalized limits for Corporate user(Rs. 500) for 'Fund Transfer' transaction type | ADMIN Dashboard>>Customer Entitlements>>User Maintenance>>Enter User Login ID Details>>Search>>Select 'Personalized Limits' from 'More Actions' Dropdown>>OK>>Create New | System should allow user to set personalized limits for Corporate user for payment transaction type | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC028 | Customer Entitlements | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of beyond corporate and user personalised limit (Rs. 510) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer of beyond corporate and user personalised limit and display proper error message | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC029 | Customer Entitlements | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer of below corporate and user personalised limit (Rs. 20) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should allow user to do fund transfer of below corporate and user personalised limit | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16
IDBI intech |  | TC030 | Paayment & Transfer | Fund Transfer | Initiate Fund Transfer | To verify if user is able to do fund transafer with setup of personalized limit | To check whether user is able to do fund transfer when daily corporate and user personalized limit exceeded (Daily Limit remains 0) | UAT Dashboard>>Menu>>Payments & Transfer>>Fund Transfer>>Initiate Fund Transfer>>NEFT and RTGS Payments | System should not allow user to do fund transfer when daily corporate and user personalized limit exceeded and display proper error message | pass |  |  |  |  | shubhangi Darade | 2019-07-12 | 2019-07-16 |  |  |  |  | 2019-07-16

## Sheet2
25
66